## Sheet1
Issue Name | Details | Comment
Subscription
sign up | 1. in sign up page, if password doesnot match with confirm password , both field should be cleaned after clicking signup button -Done 2.i sign up by Test01…. Email but it says this email already exist,though test01…. Email never been used -Done
login | 1. login password error message should change -Done 2. once login by google or fb no option to use other google or fb id. -Done only google 3.after logout user name and password remains in sign in page. -Done 4. erorr message when pressed in log in without password must change . -Done 5.sign up page remains after log out from recent signing up -Done
Change password | 1. processing continues when old password is given wrong at the time of chamging password. -Done 2.change password erorr message not ok when old password is given wrong. 3. password field should be cleaned up after erorr -Done
credit | 1. if user buy credit from fax sending page , no credit adds in setting page. But user can send fax. -Done 2. after sending credit balance remains unchanged -Done 3.lost credit in new biuld -Done 4.i had 700 credit I sent 2 and then 4 page , credit sould be 640 but credit is 620. once it becomes 0 by sending one page
History | 1. History page better have clear option. -No need 2.send a image and backward from app , then go to app , the last sending image history takes time to processeing.
forget password | 1. not working -Done
Image | 1. delete selected images but there is a view problem .