## Sheet1
project name | Call recorder
Developer name | Hemal Khan
Created by | Fahad Hossain Akash
Created date
Test ID | Test scenario name | Test scenario ID | Test scenario description | Test case description | Test steps | Test data | Expected result | Actual result | Status | Executed by | Executed date | Devices used | Comments | test case recording
1 | Edit screen | 50003 | Edit screen design is impleneted according to approved design | All buttons, word are as same as approved design | match home screen design with approved design | no needed | edit screen design will be as same as approved design | edit screen design is as same as approved design | passed | Fahad Hossain Akash | 2019-02-09 | iphone 5s
|  | 15504 | iamge pick from gallery | user can pick image to from gallery to make slide show video | click new button from edit screen. Gallery screen will be open. Select images. Click done button | no needed | all selected images will be displayed on edit screen and slide show will be palyed | all selected images have been displayed on edit screen and slide show has been palyed | passed | Fahad Hossain Akash | 2019-03-09 | iphone 5s iphone X ipad | 1. 100 and 50 images are picked from gallery and saved the slide show 2. slide show of 100 & 50 image are run successfully in pc 3. image is also selected by taking photos from camera of the gallery | iphone: https://drive.google.com/open?id=1_HDfX_WlXZJWGZcilPDZhbIwt7XKmBRh ipad: https://drive.google.com/open?id=1EGxvSS6_mD5klkREkW8CswthCgx3oWU_
|  | 25504 | add theme in slide show | user can add theme from theme option, there are many different type of themes | click new button from edit screen. Gallery screen will be open. Select images. Click done button. Slide show video will be created. Regular theme will be selected by default. Now click on other themes | no needed | video will be played according to what theme will be selected | video is being played according to selected theme | passed | Fahad Hossain Akash | 2019-03-09 | iphone 5s iphone X | 1. all themes are tested with implementing 2. added themes are saved and shared successfully (fb,messanger,instagram) 3. time duration is as same as edited | iphone X: https://drive.google.com/open?id=153QkzsjlU2DZKEFMyaoI8IJgXsEg81L-
|  |  | add duration in the video | user can change the video duration of the slide show video from suration option | click new button from edit screen. Gallery screen will be open. Select images. Click done button. Slide show video will be created. Now click on duration option, change the duration. Loading view will come | no needed | video will be played according to what duration will be selected | video is being played according to selected duration | passed | Fahad Hossain Akash | 2019-03-09 | iphone 5s iphone X | 1. time duration is as same as edited after save & share 2. slide video is created with adding song and theme
|  |  | add sound effect in the video | user can add sound effect from music option | click new button from edit screen. Gallery screen will be open. Select images. Click done button. Slide show video will be created. Now click on music option. Choose any sound effect (itunes,track,record) | no needed | after Choosing sound effect, tune will be added in the video and tune will be played with slide show | tune is added in the video and tune is being played with slide show | passed | Fahad Hossain Akash | 2019-03-09 | iphone 5s iphone X | 1. created video is saved 2. time duration is as same as edited after save & share
|  |  | add sound effect from itunes | user can add sound effect from itunes of music option | click new button from edit screen. Gallery screen will be open. Select images. Click done button. Slide show video will be created. Now click on music option.click on itunes. Itunes screen will be open. Choose any tune from itunes | no needed | after Choosing sound effect, tune will be added in the video and tune will be played with slide show | tune is added in the video and tune is being played with slide show | passed | Fahad Hossain Akash | 2019-03-09 | iphone 5s iphone X | 1. created video is saved 2. time duration is as same as edited after save & share
|  |  | add sound effect from tracks | user can add sound effect from tracks of music option | click new button from edit screen. Gallery screen will be open. Select images. Click done button. Slide show video will be created. Now click on music option.click on tracks. A screen of list of music folder will be open. Click any folder, a list of song will be open. click on any song file. if the selected song file is not clicked before it will started progress hood, then it will be palying when progress hood is completed. now click on 'use this track' button. user can click on this button if the selected fileprogress hood mood. a pop up screen of downloading this file will come. after completing download, song will be added to to video. if the song is used before then no pop up screen of downloading will come, the song will be directly added to to video. | no needed | after adding song, song will be added in the song will be played with slide show | song is being played with slide show | passed | Fahad Hossain Akash | 2019-03-09 | iphone 5s iphone X | 1. created video is saved 2. time duration is as same as edited after save & share
|  |  | add voice from record | user can add voice record from record of music option | click new button from edit screen. Gallery screen will be open. Select images. Click done button. Slide show video will be created. Now click on music option.click on record. Recording screen will come. Click on start reecord button. It will started recording according to video duration, user can stop recording any time by himself | no needed | after adding voice rec, recording will be added in the song will be played with slide show | recording has been added in the song will be played with slide show | passed | Fahad Hossain Akash | 2019-03-09 | iphone 5s iphone X | 1. created video is saved 2. time duration is as same as edited after save & share
2 | server value check | 51503 | subshome will be displayed when lauching the app | user will find subs home when launch the app | laucnh the app first. Make sure the app in unsybscribed and deleted from background | subshome=1 devce time/region = non blocklist country | user will find subs home | user has found subs home | passed | Fahad Hossain Akash | 2019-02-09 | iphone X ipad | 1. no subs home when subs home = 0 2. subshome is without cross button according to extra colunm 4= 1 | iphone X: https://drive.google.com/open?id=1MaMkBpT_1nYiOsKcN_VNyzzhRdgxGZ4Z ipad: https://drive.google.com/open?id=1_ebl-C262K-JKnUZ65Dj3rtcexNbXkpL
|  | 54503 | force review will come against subs page | user will find force review against subs page | click on any unsubscribe feature of the app. Subs page will come. Now click on cross button of subs page | review unlock = 1 isApprv = 1 devce time/region = non blocklist country | force review will come against cross button of subs page | force review has come against cross button of subs page | passed | Fahad Hossain Akash | 2019-02-09 | iphone X ipad | 1. user is subscribed after giving force review 2. no force review against subs page after giving force review 3. no force review if rev unlock or isApprv is 0 4. OS reivew comes after every 2nd save.this is tested | iphone X: https://drive.google.com/open?id=1NtVTxOnskZfkO9w80LaoxI_J_wtoyLEK ipad: https://drive.google.com/open?id=1sxMQt_UeK8wm00keT8mPRmYgWJBtPR8Z app puchase after review: https://drive.google.com/open?id=1nsrkRAbLgTSfKCW8Sb3Z8HZbWJnRw9eI
|  | 113004 | free save and share some slide shows | user can save and share some slide shows free | create slide show video. Click save button and the video will be saved.save and share screen will come. Let the saving process be completed. This saving process will count the server value(free save) | extra column 1 = number of free save ( 2 for iphone x & 3 for ipad) | user can save and share some slide shows free according to server value | user has saved and share some slide shows free according to server value | passed | Fahad Hossain Akash | 2019-03-09 | iphone X ipad | 1. after limit is crossed, subs page will come. 2. saved from any screen is tested 3. 'free save is over' this message is being showed against save button 4. if save button is clicked by selecting pro theme, 'free save is over' subs page will not being showed | iphone x: https://drive.google.com/open?id=1FjVFR5nvpR6K1g2K_FD9iXxVxQmwLbcO ipad: https://drive.google.com/open?id=1Dp7pQnOtWDGOQb8ZBWfyMKeh9rMuQvZU
|  | 40004 | subs button change according to server value | user will find subs button according to server value | make extra column 2 = 1 for start free trial or make extra column 2 = 0 for subscribe now | extra column 2 = 1/0 is Apprv = 1 | if extra column 2 = 1, button is start free trial if extra column 2 = 0, button is subscribe now | button is start free trial for extra column 2 = 1 button is subscribe now for extra column 2 = 0 | passed | Fahad Hossain Akash | 2019-03-09 | iphone X ipad | 1. all actions of both button are same 2. button will not be start free trial if isApprv = 0 | iphone X: https://drive.google.com/open?id=1fiuY2xhGS_o5B4q09PZGS8OUn3qA4KEH
3 | subscription and its functionality | 34504 | subs page design is impleneted according to approved design | All buttons, word are as same as approved design | match subs screen design with approved design | no needed | subs screen design will be as same as approved design | subs screen design is as same as approved design | passed | Fahad Hossain Akash | 2019-03-09 | iphone X ipad iphone 5s | 1. on boarding iamges display are bug free
|  | 41504 | subs cross button dismisses the subs page | user can dismiss the subs page by pressing cross button of subs page | open subs page. Click on cross button of subs page | no needed | subs page will be dismissed | subs page has been dismissed | passed | Fahad Hossain Akash | 2019-03-09 | iphone X ipad iphone 5s |  | iphone X: https://drive.google.com/open?id=1PhURr448CO9cHwdru8J6o11rffhcKq47
|  | 73504 | subs info is as same as price button | user can find subs info at the bottom of the subs page | open subs page. Read the subs info at the bottom. Match the price and free trial day of the button and subs info | no needed | subs info will be as same as price button | subs info is as same as price button | passed | Fahad Hossain Akash | 2019-03-09 | iphone X ipad iphone 5s | 1. there are 2 buttons, privacy policy and terms. Both are chekced, they open there own links in safari.both are checked in data off mood
|  | 52004 | subscribe the app by subscription button | user can subscribe the app by subscription button | open subs page from any part of the app, click on subs button. Complete all popup message requirments operation.after completing, you are all set popup messge will appear. Click ok button of popup message | no needed | after clicking ok, app will be purchased | app is purchased | passed | Fahad Hossain Akash | 2019-03-09 | iphone 5s ipad | 1. subscription is done from both button 2. after subscribe the app, all lock features are open and no subshome or forcec review is being showed 3. subscription auto expired successful | iphone 5s: https://drive.google.com/open?id=1-j9OlgEwksviGwtE7dd5LILwvWlFqr-l ipad:
|  | 62004 | restore the subscription | user can restore the subscription by restore button | install unsubscribed app. Open subs page. Click on restore button. | app should have subsription validation and device should be login with the subscribed id | if app id has the subscription validity, app will be purchased | app is purchased | passed | Fahad Hossain Akash | 2019-03-09 | iphone 5s | 1. if app has no subscription validity, subs failed popup message will come 2. if the app has never been purchased, nothing to restore message will come 3. restore button is checked in data off mood 4. app is auto subscribed if app has subscription validation | iphone 5s: https://drive.google.com/open?id=1Nr_6Jpf1aKZzha93YRgUusNOfpNCd1yf
|  | 111005 | subscription expired | user will be expired after the end of subscription validation | purchase the app. Wait for the end of the purchase validation | device should be login with the subscribed id | when subscription validation is over, app will be unsubscribed | app is unsubscribed | passed | Fahad Hossain Akash | 2019-04-09 | iphone 5s ipad | 1. after unsubscribed, all features will be locked and subshome, free save limit will work according to server value