## Sheet1
project name | Call recorder
Developer name | Hemal Khan
Created by | Fahad Hossain Akash
Designer | Raj Raj
Created date
Test ID | Test scenario name | Test scenario ID | Test scenario description | Test case description | Test steps | Test data | Expected result | Actual result | Status | Executed by | Executed date | Devices used | Comments
1 | Splash screen | 82801 | splash screen will be appeared when open the app | a spalsh screen icon will be appeared after every open the app newly.make sure the is deleted from bacground | open the app newly | no needed | a splash screen icon will be displayed when open the app | a splash screen icon has displayed when open the app | passed | fahad hossain akash | 18/4/19 | iphone 5s | 1. not tested in other devices yet. So this test case is only passed for iphone 5s
2 | First screen design and its functionality | 85501 | screen dedsign according to appreoved design | all butons,buttons design,desriptions on the screen is as same as approved design | open approved design and app design. Now match both of design | no needed | app design will be as same as approved design | app design is as same as approved design | passed | fahad hossain akash | 18/4/19 | iphone 5s | 1. not tested in other devices yet. So this test case is only passed for iphone 5s | important note: call recording save test was again asked to test for changing server. The test is done and recording saved.
|  | 91401 | privacy policy button and its functionality | click privacy policy button and privacy policy web view will be open | click privacy policy button. Make sure the device is data onnected | no needed | privacy policy web view will be open and privacy policy description will be displayed on safari | privacy policy web view has open and privacy policy description has displayed on safari | passed | fahad hossain akash | 18/4/19 | iphone 5s | 1. not tested in other devices yet. So this test case is only passed for iphone 5s 2. this issue tested in data off mood. No bug found 3. priacy policy is the web view of 2nd number for testing purpose
|  | 92701 | terms button and its functionality | click terms button and privacy policy web view will be open | click termsbutton. Make sure the device is data onnected | no needed | terms web view will be open and privacy policy description will be displayed on safari | terms web view has open and privacy policy description has displayed on safari | passed | fahad hossain akash | 18/4/19 | iphone 5s | 1. not tested in other devices yet. So this test case is only passed for iphone 5s 2. this issue tested in data off mood. No bug found 3. priacy policy is the web view of 2nd number for testing purpose
|  | 93301 | "I agree" button and its functionality | click "I agree" button and Reg page will be open | click "I agree" button. This butto does not have any link with internet | no needed | Reg page will be open | Reg page has open | passed | fahad hossain akash | 18/4/19 | iphone 5s | 1. not tested in other devices yet. So this test case is only passed for iphone 5s
3 | Reg page and its functionality | 93601 | back button and its functionality | clcik back button, the Reg page will be dismissed and first screen of app will be dispalyed | clcik back button | no needed | after click back button, the Reg page will be dismissed and first screen of app will be dispalyed | after click back button, the Reg page has dismissed and first screen of app has dispalyed | passed | fahad hossain akash | 18/4/19 | iphone 5s | 1. not tested in other devices yet. So this test case is only passed for iphone 5s
|  | 94201 | country code list button and its functionality | clcik country code list button, a code list page will be displayed | clcik country code list button | no needed | a code list page will be displayed | a code list page has displayed | passed | fahad hossain akash | 18/4/19 | iphone 5s | 1. not tested in other devices yet. So this test case is only passed for iphone 5s
|  | 94801 | country code list seletion | select a certain country code and the selected country code will displayed on country code button | select a certain country code | no needed | the selected country code will displayed on country code button | the selected country code has displayed on country code button | passed | fahad hossain akash | 18/4/19 | iphone 5s | 1. not tested in other devices yet. So this test case is only passed for iphone 5s
|  | 95501 | Reg with a valid number this app | use a valid phone number to register the app | type a valid phone number on phone number type box.now click next button. Sms sending screen will be open and there will be a loading animation displayed. If internet is connected a vrification sms will be sent to that phone number.and that will said on the last screen displayed.after that verification screen will be open. type the verification code which sent by sms. now click continue | a valid phone number | the app will be verified and the local access number screen will be open | the app will be verified and the local access number screen has open | passed | fahad hossain akash | 18/4/19 | iphone 5s | 1. not tested in other devices yet. So this test case is only passed for iphone 5s 2. this reg page is functioned by facebook. So there is no possibilty to find any bug
4 | Local accees nummber screen and its fnctionality | 102001 | local number selection to call from app | select a number from this screen to call from app and record call | select a number from this screen. A message box will be prompt which will say this number will be used for call recording line number. Click ok button | no needed | after clicking ok button call recorder screen will be open | after clicking ok button call recorder screen has open | passed | fahad hossain akash | 18/4/19 | iphone 5s | 1. not tested in other devices yet. So this test case is only passed for iphone 5s 2. if click cancel button of prompt message, prompt message will be dismissed and user will remain on local number screen
5 | Home screen & its functionality | 103001 | screen dedsign according to appreoved design | All butons,buttons design,desriptions on the screen is as same as approved design | open approved design and app design. Now match both of design | no needed | app design will be as same as approved design | app design is as same as approved design | passed | fahad hossain akash | 18/4/19 | iphone 5s | 1. not tested in other devices yet. So this test case is only passed for iphone 5s
|  | 103601 | click settings button, settings screen will be displayed | Click settings button, settings screen will be displayed | click settings button | no needed | settings screen will be displayed | settings screen has displayed | passed | fahad hossain akash | 18/4/19 | iphone 5s | 1. not tested in other devices yet. So this test case is only passed for iphone 5s
|  | 104001 | click Recording screen button, Recording screen will be displayed | click Recording screen button,Recording screen will be displayed | click Recording screen button | no needed | Recording screen will be displayed | Recording screen has displayed | passed | fahad hossain akash | 18/4/19 | iphone 5s | 1. not tested in other devices yet. So this test case is only passed for iphone 5s
|  | 104401 | click app tutirial button, app tutirial screen will be displayed | click app tutorial button, app tutorial screen will be displayed | click app tutorial button | no needed | app tutorial screen will be displayed | app tutorial screen has displayed | passed | fahad hossain akash | 18/4/19 | iphone 5s | 1. not tested in other devices yet. So this test case is only passed for iphone 5s
|  | 104701 | a transparent screen of contact/keypad screen will be displayed against call record button | click call record button, a transparent screen of contact/keypad screen will be displayed | click call record button | no needed | a transparent screen of contact/keypad screen will be displayed | a transparent screen of contact/keypad screen has displayed | passed | fahad hossain akash | 18/4/19 | iphone 5s | 1. not tested in other devices yet. So this test case is only passed for iphone 5s
6 | Settings screen and its functionality | 111501 | Account screen will be open if click on Account button | click on Account button, Account screen will be open | click on Account button | no needed | Account screen will be open | Account screen has open | passed | fahad hossain akash | 18/4/19 | iphone 5s | 1. not tested in other devices yet. So this test case is only passed for iphone 5s
|  | 112001 | server access number screen will be open if click on access number button | click on access number button, Local access number screen will be open | click on access number button | no needed | Local access number screen will be open | Local access number screen has open | passed | fahad hossain akash | 18/4/19 | iphone 5s | 1. not tested in other devices yet. So this test case is only passed for iphone 5s 2. user can change server number and that will be updated In both app and phonebook (app must has the permission of access phonebook). -tested 3. without data mood user cannot change server number. -tested 4.after change the server number, user can call and record without any bug -tested
|  | 112301 | OS share screen will be displayed if click on Tell a friend button | click on Tell a friend button, OS share screen will be displayed | OS share screen will be displayed | no needed | OS share screen will be displayed | OS share screen has displayed | passed | fahad hossain akash | 18/4/19 | iphone 5s | 1. not tested in other devices yet. So this test case is only passed for iphone 5s
|  | 112901 | purchase status message box of the app will displayed against Restore button | Click on Restore button, purchase status message box of the app will displayed whether the app purchased or not. | Click on Restore button | no needed | purchase status message box of the app will displayed | purchase status message box of the app has displayed whether the app purchased or not. | passed | fahad hossain akash | 18/4/19 | iphone 5s | 1. not tested in other devices yet. So this test case is only passed for iphone 5s 2. this issue is tested without data mood. There is no bug found as a prompt message says "cannot connect to itunes
|  | 113301 | Logout from app against logout button | Click on logout button, user will be logout from app. | Click on logout button. A logout confirmation message will be prompt. Click 'yes' . | no needed | user will be logout from app. | user has logout from app. | passed | fahad hossain akash | 18/4/19 | iphone 5s | 1. not tested in other devices yet. So this test case is only passed for iphone 5s 2. this issue is tested without data mood. There is no bug found 3.if click cancel button of prompt message, prompt message will be dismissed and user will remain on Settings screen.
7 | Account screen and its functionality | 120801 | screen dedsign according to appreoved design | all butons,buttons design,desriptions on the screen is as same as approved design | open approved design and app design. Now match both of design | no needed | app design will be as same as approved design | app design is as same as approved design | passed | fahad hossain akash | 18/4/19 | iphone 5s | 1. not tested in other devices yet. So this test case is only passed for iphone 5s 2. expire duration is not tested properly as testing is going through sandbox account
|  |  | Add email | click on email button, email adding screen will be open. Type email and click save button email will be saved | click on email button, type valid email on the box(though validation not required). Now click save button | add an email format data | added email will be saved | added email has saved | passed | fahad hossain akash | 18/4/19 | iphone 5s | 1. not tested in other devices yet. So this test case is only passed for iphone 5s 2. email can be change further, even after logout and then login email will be same. This test case is tested. 3. if email format data is not typed, it shows an alert message. This test case is tested. 4. back button is tested.
8 | Subscription page design and its functionality | 31501 | subscription design accordign to approved design | all butons,buttons design,desriptions on the screen is as same as approved design | open approved design and app design. Now match both of design | no needed | app design will be as same as approved design | app design is as same as approved design | passed | fahad hossain akash | 18/4/19 | iphone 5s | 1. not tested in other devices yet. So this test case is only passed for iphone 5s
|  | 32801 | yearly subscription purchase | user will be purchased to yearly if he select yearly button and click start your free trial. | select yearly button. Now click 'start your free trial". Purchase confirmation message will be displayed. Make sure message price and button price is same and free trial is said if this purchase is first time against user id. Otherwise no free trial will be said | no needed | after clicking start button and then confirm purchase, app will be purchased and app will lead the user in local number screen | after clicking start button and then confirm purchase, app has been purchased and app is leading the user in local number screen | passed | fahad hossain akash | 18/4/19 | iphone 5s | 1. not tested in other devices yet. So this test case is only passed for iphone 5s 2. purchase button is checked in offline data mood. 3. price match is still not same as it is in under dev mood
|  | 33101 | monthly subscription purchase | user will be purchased to monthly if he select monthly button and click start your free trial. | select monthly button. Now click 'start your free trial". Purchase confirmation message will be displayed. Make sure message price and button price is same and free trial is said if this purchase is first time against user id. Otherwise no free trial will be said | no needed | after clicking start button and then confirm purchase, app will be purchased and app will lead the user in local number screen | after clicking start button and then confirm purchase, app has been purchased and app is leading the user in local number screen | passed | fahad hossain akash | 18/4/19 | iphone 5s | 1. not tested in other devices yet. So this test case is only passed for iphone 5s 2. purchase button is checked in offline data mood. 3. price match is still not same as it is in under dev mood
|  | 113803 | restoring purchase | user will restore his subscription against restore button if he bought any package from subscription page and still has the validation. If validation is over purchase will be failed | click restore button. | no needed | if user has bought any package from subscription page and still has the validation. He will get restored his package If validation is over purchase will be failed. | user has restored his subscription. If subs validation is over. Purchase gets failed. | passed | fahad hossain akash | 23/4/19 | iphone 5s iphone X | 1. not tested in other devices yet. So this test case is only passed for iphone 5s 2. restore button is checked in ofline data mood. 3. if restore button of subshome is pressed and the user is subscribed before, he will get subscribed and lead to the local number screen. 4. after subs expired is tested but need to test when subs validation is still exist
|  | 34301 | privacy policy button and its functionality | click privacy policy button and privacy policy web view will be open | click privacy policy button. Make sure the device is data connected | no needed | privacy policy web view will be open and privacy policy description will be displayed on safari | privacy policy web view has open and privacy policy description has displayed on safari | passed | fahad hossain akash | 18/4/19 | iphone 5s | 1. not tested in other devices yet. So this test case is only passed for iphone 5s 2. this issue tested in data off mood. No bug found 3. priacy policy is the web view of 2nd number for testing purpose
|  | 34801 | terms button and its functionality | click terms button and terms & privacy policy web view will be open | click terms button. Make sure the device is data onnected | no needed | terms web view will be open and privacy policy description will be displayed on safari | terms web view has open and privacy policy description has displayed on safari | passed | fahad hossain akash | 18/4/19 | iphone 5s | 1. not tested in other devices yet. So this test case is only passed for iphone 5s 2. this issue tested in data off mood. No bug found 3. terms is the web view of 2nd number for testing purpose
9 | Recording & its functionality (Outgoing) | 104002 | App will not call from invalid number | when type invalid phone unmber or pick invalid number from contact, app will say invalid phone number through an alert message | click record button In home screen, number pic screen will appear. Pick number from contact or type number from keypad. Clcik call button for keypad screen and click on number from contact | *222#,0195485,01952,*01954857634#,*019548576#,*#, 01365 all numbers are picked from contact and keypad | after picking invalid number, app will say invalid phone number through an alert message | after picking invalid number, app is saying invalid phone number through an alert message | passed | fahad hossain akash | 19/4/19 | iphone 5s | 1. not tested in other devices yet. So this test case is only passed for iphone 5s
|  | 122004 | Record a call when call from contact list and then app is open or call to server number to record | user can record in the middle a conversation, during conversation he can call to recording server from app or contact list to record the call | call any local number. During conversation, call to recording server from app or contact list to record the call. Now click merge after the server beep is confirmed | multiple valid phone number to call | after clicking merge button, conversation will be being recorded till finish the conversation. When it is finished recording will be saved to recording folder of app. | after clicking merge button, conversation is being recorded till finish the conversation. When it is finished recording has saved to recording folder of app | passed | fahad hossain akash | 30/4/19 | iphone 5s | 1. not tested in other devices yet. So this test case is only passed for iphone 5s and iphone X.
|  | 105502 | Record a call when device sim number and app verified number is same | User will call a number and record their conversastion. After finishing the conversation, recording will be saved in app recording folder | click record button from home screen. Choose any path to call a number. Server number will be prompt to call. Click call button, now call conversation screen will be appeared. After server connection succesfull , it will ask to call users desired number to dial through prompt a message box.click call and then the nunmbr will be rang. when receiver will receive the number user has to click on merge on call conversation screen.and then recording will be started. make sure device sim number and app verified number is same | a valid phone number to call | after clicking merge button, conversation will be being recorded till finish the conversation. When it is finished recording will be saved to recording folder of app. | after clicking merge button, conversation is being recorded till finish the conversation. When it is finished recording has saved to recording folder of app | passed | fahad hossain akash | 19/4/19 | iphone 5s iphone X | 1. not tested in other devices yet. So this test case is only passed for iphone 5s and iphone X. 2. this test case is tested with earphone plugged in.
|  | 112002 | Record a call when device sim number and app verified number is not same | User will call a number and record their conversastion. After finishing the conversation, recording will be not saved in app recording folder. But the recorded file will be found in device sim number verified account | click record button from home screen. Choose any path to call a number. Server number will be prompt to call. Click call button, now call conversation screen will be appeared. After server connection succesfull , it will ask to call users desired number to dial through prompt a message box.click call and then the nunmbr will be rang. when receiver will receive the number user has to click on merge in call conversation screen.and then recording will be started. make sure device sim number and app verified number is not same | a valid phone number to call | after clicking merger button, conversation will be being recorded till finish the conversation. When it is finished recording will not be saved to recording folder of app. | after clicking merger button, conversation is being recorded till finish the conversation. When it is finished recording has not saved to recording folder of app | passed | fahad hossain akash | 19/4/19 | iphone 5s iphone X | 1. not tested in other devices yet. So this test case is only passed for iphone 5s and iphone X. 2. in this test case both devices are used for two account using. Two account is used in two devices with vice versa 2. this test case is tested with earphone plugged in.
|  | 114802 | Record a call when device sim number and app verified number is not same and the recording will not be saved in the app. But the recording will be found in sim number verified account | User will call a number and record their conversastion. After finishing the conversation, recording will be not saved in app recording folder. But the recorded file will be found in device sim number verified account | click record button from home screen. Choose any path to call a number. Server number will be prompt to call. Click call button, now call conversation screen will be appeared. After server connection succesfull , it will ask to call users desired number to dial through prompt a message box.click call and then the nunmbr will be rang. when receiver will receive the number user has to click on merge in call conversation screen.and then recording will be started. make sure device sim number and app verified number is not same. now check app recording folder. the recorded file will not be found. now logout from app and login to device sim number verified account. | a valid phone number to call | after login to device sim number verified account, go to app recording screen. Here the recorded file will be found | after login to device sim number verified account, go to app recording screen. Here the recorded file has been found | passed |  | 19/4/19 | iphone 5s iphone X | 1. not tested in other devices yet. So this test case is only passed for iphone 5s and iphone X. 2. in this test case both devices are used for two account using. Two account is used in two devices with vice versa 3. through this test case I login same account in two devices and check the recorded files in recording folder and found both device files are same. 2. this test case is tested with earphine plugged in.
|  | 113004 | call record when create a group conversation call (incomng) | User can add people from call conversation screen to make group conversation. If conversation is merged, call will be recorded | add one or more people in a single call conversation. | valid phone numbers | the group call conversation will be recorded untill finish the call | the group call conversation has recorded untill finish the call and saved in app recording file | passed | fahad hossain akash | 30/4/19 | iphone 5s | 1. not tested in other devices yet. So this test case is only passed for iphone 5s and iphone X. 2. in converesastion, 4th party is rishivai
|  | 121004 | call record when create a group conversation call (outgoing) | User can add people from call conversation screen to make group conversation. If conversation is merged, call will be recorded | add one or more people in a single call conversation. | valid phone numbers | the group call conversation will be recorded untill finish the call | the group call conversation has recorded untill finish the call and saved in app recording file | passed | fahad hossain akash | 30/4/19 | iphone 5s iphone X | 1. not tested in other devices yet. So this test case is only passed for iphone 5s and iphone X. 2. in converesastion, 4th party is rajvai
|  | 121502 | Record a call when call from contact list | if user call from contact list manually, he can also record conversation even app is in background or delete from bacground. The recording will be saved | dial server number from device contact or device keypad(if number is not saved). As usual it will connect to server line and when server will alert with a voice speech of starting record, click + button from call conversation by which user can call his desired number. after dial and receive the call from the other end, click merge button. | a valid phone number to call | after finishing the call, recording will be saved in app recording folder. | after finishing the call, recording is saved in app recording folder. | passed | fahad hossain akash | 19/4/19 | iphone 5s iphone X | 1. not tested in other devices yet. So this test case is only passed for iphone 5s and iphone X.
10 | Recording & its functionality (incoming) | 22502 | Record a call when device sim number and app verified number is same | when a call incoming, user can record the call from app | when incoming call is received, go to device home screen. Now open app and click on record button. It will ask to call its server number. Click call. Call conversation screen will be open. Now after the server beep for recording click on merge. | a valid phone number to call | after click on merge button, call conversation will be recording untill conversation is over. The recorded audio file will be saved in app recording folder | after click on merge button, call conversation is recorded untill conversation is over. The recorded audio file has saved in app recording folder | passed | fahad hossain akash | 19/4/19 | iphone 5s iphone X | 1. not tested in other devices yet. So this test case is only passed for iphone 5s and iphone X. 2. this test case is tested when app is in background or deleted from background
11 | Recording screen and its functionality | 30502 | screen dedsign according to appreoved design | all buttons design, file formate, desriptions on the screen is as same as approved design | open approved design and app design. Now match both of design | no needed | app design will be as same as approved design | app design is as same as approved design | passed | fahad hossain akash | 19/4/19 | iphone 5s iphone X | 1. not tested in other devices yet. So this test case is only passed for iphone 5s and iphone X.
|  | 32002 | Audio file play in recording screen | call recorded file can be played in recording screen | go to recording screen of app. There should be some recorded files which are recorded from app. If reorded file is not downloaded yet click on the file. It will be loading while downloading. Or if the file is already downloaded just click on the file | no needed | after finishing the download or click on the downloaded file, the audio file will start playing. | after finishing the download or click on the downloaded file, the audio file is started playing. | passed | fahad hossain akash | 19/4/19 | iphone 5s iphone X | 1. not tested in other devices yet. So this test case is only passed for iphone 5s and iphone X. 2. recorded file date and time is checked date and time is saved according to device date and time.
|  | 40002 | Play button | when click on any recording file, paly button will be changed to play. User can pause or play audio file by this button. | play a recording file | no needed | play button will be changed to play. User can pause recording through this button | play button has changed to play. User can pause recording through this button | passed | fahad hossain akash | 19/4/19 | iphone 5s iphone X | 1. not tested in other devices yet. So this test case is only passed for iphone 5s and iphone X.
|  | 122303 | palyer Slider | when recording will be playing, silder will also be playing in pulse formate. | play a recording file | no needed | player slider will be playing in pulse formate. | player slider is playing in pulse formate. | passed | fahad hossain akash | 25/4/19 | iphone 5s iphone X | 1. not tested in other devices yet. So this test case is only passed for iphone 5s and iphone X.
|  | 25204 | Audio file will be speed up and down by Speed button | while playing any file, if user play seep button, the current playing file will be speeded up-down according to 1x to2x,3x and 0.5x if no audio is playing the button wont change | play a recording file | no needed | after click the speed button playing file will be speeded up-down according to 1x to2x,3x and 0.5x | after click the speed button playing file has speeded up-down according to 1x to2x,3x and 0.5x | passed | fahad hossain akash | 30/4/19 | iphone 5s iphone X | 1. not tested in other devices yet. So this test case is only passed for iphone 5s and iphone X.
|  | 121503 | playing forward and backward by using Forward and backward button | user can go 15s Forward or backward button by using Forward and backward button. If play is of user can still move Forward or backward | play a recording file | no needed | after clicking forward or backward button user will move to 15s Forward or backward. no matter audio is playing or not. And the time limitation of audio file. | after clicking forward or backward button can move to 15s Forward or backward | passed | fahad hossain akash | 25/4/19 | iphone 5s iphone X | 1. not tested in other devices yet. So this test case is only passed for iphone 5s and iphone X.
|  | 125003 | Share recording file by share button | User can share recording files by share button. OS share option will be popped upa aginst this button | click on share button. OS share option will be popped upa aginst this button. Then choose share option. | recorded file which is saved in app | reocrding file will be shared according to users share choice | reocrding file has been shared according to users share choice | passed | fahad hossain akash | 25/4/19 | iphone 5s iphone X | 1. not tested in other devices yet. So this test case is only passed for iphone 5s and iphone X.
12 | server API value check | 123305 | subs home is showed with cross button according to server value | subs home will be displayed after launching the app with no cross button | Fresh launch the app. Make sure device time and region is not in block list country | Subs Home = 1, extra column 4 = 0 | subs page will be displayed after launching the app | subs page has displayed after launching the app | passed | fahad hossain akash | 16/5/19 | iphone 5s iphone X | 1. this test case is tested in data off mood for both if subs home = 0/1. 2. if subs home = 0, no subs page will be displayed 3. user will be subscribed after subscribe from subs home 4. no subshome in block list country
|  | 123705 | subs home is showed with no cross button according to server value | subs home will be displayed after launching the app with no cross button | Fresh launch the app. Make sure device time and region is not in block list country | Subs Home = 1, extra column 4 = 1 | subs page will be displayed after launching the app | subs page has displayed after launching the app | passed | fahad hossain akash | 16/5/19 | iphone 5s iphone X | 1. this test case is tested in data off mood for both if subs home = 0/1. 2. if subs home = 0, no subs page will be displayed 3. user will be subscribed after subscribe from subs home 4. no subshome in block list country
|  | 125505 | force review will be showed according to server value for home screen button | if force review condition is true and app is not subscribed then forece review will be displayed against record button in home screen | open the app, click record button of home screen. Make sure device time and region is not in block list country | is apprv = 1, review ulock = 1,extra | force review will be displayed after clicking record button of home screen | force review has been displayed after clicking record button of home screen | passed | fahad hossain akash | 16/5/19 | iphone 5s iphone X | 1. if review condition is false, subs page will be displyaed against recording button -tested 2. after giving force review, user can call according to E. C. 3 = value . But the app is not subscribed. -tested 3. no force review in block list country
|  | 110206 | force review will be showed against recording file in saved recording screen | if force review condition is true and app is not subscribed then forece review will be displayed against recording file in saved recording screen. | open the app, click recording file in saved recording screen to play. Make sure device time and region is not in block list country | is apprv = 1, review ulock = 1, | force review will be displayed after clicking the saved recording file | force review has been displayed after clicking the saved recording file | passed | fahad hossain akash | 17/5/19 | iphone 5s iphone X | 1. after installing the app this test case tested on a registered number which already has some recording file. That means the app is reinstalled and login with registered number. 2. no force review in block list country
|  | 21205 | Subs page will be showed according to server value for recording file in saved recording screen | if force review condition is true and app is not subscribed then subs page will be displayed against recording file in saved recording screen after crossing free file playing | open the app, click recording file in saved recording screen to play.After finishing free limit, press any file. | force review condition is false, extra column 4 = free rec file play value | subs page will be displayed after clicking the saved recording filee | subs page will be displayed after clicking the saved recording file | passed | fahad hossain akash | 16/5/19 | iphone X | 1. after installing the app this test case tested on a registered number which already has some recording file. That means the app is reinstalled and login with registered number.
13 | Push notication for outgoing call | 93107 | push notification is showed in app | after finishing conversation, push notification is showed in app | call from app and record the conversation as usual. Finish the call. Make sure notification show is allow from device settings | no needed | push notification will be showed in app | push notification is showed in app | passed | fahad hossain akash | 27/5/19 | iphone 5s iphone X | 1. this test case is done in data off mood. After finishing the call when data is on, notification comes even in saved file. 2. this test case is tested from server value increasing not after subscribed because dev says app cannot be purchased on that moment
|  | 93907 | push notification is showed in bacground | after finishing conversation, push notification is showed in bacground | call from app and record the conversation as usual.during conversation delete the app from background. Finish the call. Make sure notification show is allow from device settings | no needed | push notification will be showed in background | push notification is showed in background | passed | fahad hossain akash | 27/5/19 | iphone 5s iphone X | 1. this test case is done in data off mood. After finishing the call when data is on, notification comes even in saved file. 2. this test case is tested from server value increasing not after subscribed because dev says app cannot be purchased on that moment
|  | 101007 | push notification is showed in lockscreen | after finishing conversation, push notification is showed in lockscreen | call from app and record the conversation as usual. Finish the call. Somehow let the device go to sleep mood or lockscreen. Make sure notification show is allow from device settings | no needed | push notification will be showed in lockscreen. | push notification is showed in lockscreen. | passed | fahad hossain akash | 27/5/19 | iphone 5s iphone X | 1. this test case is tested from server value increasing not after subscribed because dev says app cannot be purchased on that moment 2. this test case is tested from server value increasing not after subscribed because dev says app cannot be purchased on that moment
|  | 95007 | push notification is showed in bacground when call from phonebook | after finishing conversation, push notification is showed in lockscreen when call from outside of app | call from phonebook and record the conversation as usual. Finish the call. Make sure notification show is allow from device settings | no needed | push notification will be showed in background or if goes to app, then will be showed in app but this is almost not possible because of showing notification too earlier | push notification is showed in background or in app | passed | fahad hossain akash | 27/5/19 | iphone 5s iphone X | 1. this test case is done in data off mood. After finishing the call when data is on, notification comes. 2. this test case is tested from server value increasing not after subscribed because dev says app cannot be purchased on that moment
14 | Push notication for incoming call | 101507 | push notification is showed in app | after finishing conversation, push notification is showed in app | receive incoming call. Go to bacground from conversation screen. Open the call record app. Call to server number. conversation screen will open again. After the beep merge the call | no needed | push notification will be showed in app after finishing the call | push notification is showed in app after finishing the call | passed | fahad hossain akash | 27/5/19 | iphone 5s iphone X | 1. this test case is done in data off mood. After finishing the call when data is on, notification comes. 2. this test case is tested from server value increasing not after subscribed because dev says app cannot be purchased on that moment
|  | 102007 | push notification is showed in bacground | after finishing conversation, push notification is showed in bacground | receive incoming call. Go to bacground from conversation screen. Open the call record app. Call to server number. conversation screen will open gain. After the beep merge the call. During conversation, go to bacground from conversation screen. Finish the call | no needed | push notification will be showed in background | push notification is showed in background | passed | fahad hossain akash | 27/5/19 | iphone 5s iphone X | 1. this test case is done in data off mood. After finishing the call when data is on, notification comes. 2. this test case is tested from server value increasing not after subscribed because dev says app cannot be purchased on that moment
|  | 95508 | push notification is showed in lockscreen | after finishing conversation, push notification is showed in lockscreen if phone is screened lock before push notification comes | receive incoming call. Go to bacground from conversation screen. Open the call record app. Call to server number. conversation screen will open again. After the beep merge the call. Finish the call and screen lock the phone or go to device sleep mood before push notification comes | no needed | push notification will be showed in lockscreen. | push notification is showed in lockscreen. | passed | fahad hossain akash | 28/5/19 | iphone 5s iphone X | 1. this test case is tested from server value increasing not after subscribed because dev says app cannot be purchased on that moment
15 | recording file update through push notification for incoming call | 100508 | recording file update through push notification | recording file will be updated through push notification that comes in app background | receive incoming call. Go to bacground from conversation screen. Open the call record app. Call to server number. conversation screen will open gain. After the beep merge the call. During conversation, go to bacground from conversation screen. Finish the call. push notification will come. press the notification, app will be open to saved file screen. | no needed | saved file screen will be updated with the last recording file | saved file screen is updated with the last recording file | passed | fahad hossain akash | 28/5/19 | iphone 5s iphone X | 1. saved file screen is also updated through push notification from background 2. this test case is tested from server value increasing not after subscribed because dev says app cannot be purchased on that moment
16 | recording file update through push notification for outgoing call | 101508 | recording file update through push notification | recording file will be updated through push notification that comes in app background | call from app and record the conversation as usual.during conversation delete the app from background. Finish the call. push notification will come. press the notification, app will be open to saved file screen. | no needed | saved file screen will be updated with the last recording file | saved file screen is updated with the last recording file |  | fahad hossain akash | 28/5/19 | iphone 5s iphone X | 1. saved file screen is also updated through push notification from background 2. this test case is tested from server value increasing not after subscribed because dev says app cannot be purchased on that moment
17 | OS review | 102508 | OS review comes in app after push notification inside app | OS review comes after the push notification | after the push notification is showed in app, wait for dismissing the notification or press the notification | no needed | OS review will appear after dismissing or pressing the notification | OS review has appeared after dismissing or pressing the notification | passed | fahad hossain akash | 28/5/19 | iphone 5s iphone X | this test case is tested for both incoming and outgoing
|  | 103008 | OS review comes in app after push notification of background | OS review comes is app after the push notification which comes in background | after the push notification is showed in bacground press the notification. App will be open to saved file screen | no needed | OS review will appear saved file screen | OS review has appeared saved file screen | passed | fahad hossain akash | 28/5/19 | iphone 5s iphone X | this test case is tested for both incoming and outgoing