## Sheet1
project name | vpn4iphoneMoonvai
Developer name | Khairul Islam
Designer name | Raj Raj
Created by | Fahad Hossain Akash
Created date | 20/6/19
Test ID | Test scenario name | Test scenario ID | Test scenario description | Test case description | Test steps | Test data | Expected result | Actual result | Status | Executed by | Executed date | Devices used | Comments | Test case recordign
1 | Home screen and its functionality | 35001 | Home screen design is impleneted according to approved design | All buttons, word/sentence, map, pin position is as same as approved design | match home screen design with approved design | no needed | Home screen design will be as same as approved design | Home screen design is as same as approved design | passed | Fahad Hossain Akash | 20/6/19 | Iphone X
|  | 40001 | country list against change button | country list will be displayed against change button | click on Change button | no needed | country list will be displayed against change button | country list is displaying against change button | passed | Fahad Hossain Akash | 20/6/19 | Iphone X |  | iphone X: https://drive.google.com/file/d/10H5M8vTZX_mMTjFFXQrs-80gRJ7bCXjv/view?usp=sharing ipad:
|  | 41501 | seetings screen opens against settings button | if setting button is clicked, settings screen will be open | click on settings button | no needed | seetings screen wiil be open against settings button | seetings screen opens against settings button | passed | Fahad Hossain Akash | 20/6/19 | Iphone X |  | iphoneX: https://drive.google.com/file/d/1DlDje20Pc4yNRVZkoP1_dt_QvdtChquD/view?usp=sharing ipad:
|  | 42501 | flag image will be dislayed or changed according to server selection | flag position will be change according to which server user has selected | connect any server from country list or just click on connect button. Do it from country list several times | no needed | flag image will be change every time according to server selection | flag image is changing every time according to server selection | passed | Fahad Hossain Akash | 20/6/19 | Iphone X |  | iphone X: https://drive.google.com/file/d/15W23SoJPs46voqUhxhAg3xolw3iIUjZc/view?usp=sharing
|  | 43501 | pin position animation | pin position will be animated after connecting the vpn server | connect any server. | no needed | after server is connected, pin position will be animated | after server is connected, pin position is animating | passed | Fahad Hossain Akash | 20/6/19 | Iphone X | 1. if server is not connected, pin position is not animated, this issue is tested | iphone X: https://drive.google.com/file/d/1cicoYjepTt5Nre6vXyIAQPpnWTnZUkpd/view?usp=sharing
|  | 44501 | connect button functionality | user can connect or disconnect by this connect button | click on button when vpn is not connected or vpn is connected | no needed | if server is connected, button will be disconnected after clicking on this button if server is disconnected, button will be connected after clicking on this button | button is disconnected after clicking on this button button is connected after clicking on this button | passed | Fahad Hossain Akash | 20/6/19 | Iphone X | 1. disconnected word will be displayed if server is not connected, this issue is tested 2. connected word will be displayed if server is not disconnected, this issue is tested 3. connecting word will be displayed while server is connecting, this issue is tested | iphone X: https://drive.google.com/file/d/1J1zKq0vmAuvCGjOtXPRo9uMXKHaT6RrS/view?usp=sharing
2 | settings screen and its functionality | 50001 | Design should match with final approved design | settings screen design should match with final approved design | check color, sentece, textbox, button with final approved design | no needed | screen should match with final approved design | screen is matching with final approved design | passed | Fahad Hossain Akash | 20/6/19 | Iphone X | No comments
|  | 51001 | Support button | user can send his opinion or any bug report from this support button through email. | click this button, email page will be open.there will be Default email address, device info, subject | no needed | user can send his opnion or bug report | user can send his opnion or bug report | passed | Fahad Hossain Akash | 20/6/19 | Iphone X | 1. email header name is according to app name 2. email address is inventive apps(not sure it is final or not) 3. version is 1.6 in subject(not sure it is final or not)
|  | 50501 | Rate app | user can rate app through this burron in appstore | click this button, appstore will be open with the app account | no needed | appstore will be open with the app account. User can write review | appstore will be open with the app account. User can write review | passed | Fahad Hossain Akash | 20/6/19 | Iphone X | 1. this test case is tested in offline. No issue found
|  |  | privacy policy | user can get privacy policy of this app | click this button, privacy policy page will be open | no needed | user can read privacy policy of this app | user can read privacy policy of this app |  | Fahad Hossain Akash |  | Iphone X
|  |  | terms of service | user can get terms of service of this app | click this button, terms of service page will be open | no needed | user can read terms of service of this app | user can read terms of service of this app |  | Fahad Hossain Akash |  | Iphone X
|  |  | subs info | user can get subs info of this app | click this button, subs info page will be open | no needed | user can read subs info of this app | user can read subs info of this app |  | Fahad Hossain Akash |  | Iphone X
|  |  | store | user can get subs page of this app | click this button, subs info page will be open | no needed | user can read subs page of this app | user can read subs page of this app |  | Fahad Hossain Akash |  | Iphone X
3 | subs page and its functionality | 32002 | Design should match with final approved design | subs page design should match with final approved design | check color, sentence, button with final approved design | no needed | screen should match with final approved design | screen is matching with final approved design | passed | Fahad Hossain Akash | 2019-02-07 | iphone 5s iphone X ipad
|  | 34002 | subscribe the app | user can subscribe the app from 'subscribe now' button | click on 'subscribe now' /'start free trail' button. User id and password will be asked. Provide all needed info. After correct User id and password is given. | valid user id and password | After correct User id and password is given, user will be subscribed | user is subscribed | passed | Fahad Hossain Akash | 2019-02-07 | iphone 5s iphone X ipad | 1. price is not matching, it will be corrected before up the app 2. free trial pop up not able to found due to lack of new id | iphone X: https://drive.google.com/open?id=1FxBghlICuDN3bokEWPETS5NVF93jwBmD ipad: https://drive.google.com/open?id=1mdCf3QHfU60ZF6PVpEGBtKwn4aPFNLCW iphone 5s: https://drive.google.com/open?id=1tcfynLbqD5gooyx6gt7ZW-ZtiGKDfoFu
|  | 34502 | restore success | if user id has subscription, user can restore his purchase | click on restore button, make sure the app is fresh downloaded an user id is the one which was used for purchase. And the the id must have purchase validation | valid user id and password | if user id has validated subscription, user will get restored his purchase | user has got restored his purchase | passed | Fahad Hossain Akash | 2019-02-07 | iphone 5s iphone X ipad |  | iphone X: restoreManually: https://drive.google.com/open?id=1Ul7g8-qKoomHozUBPpA3GCl5-OWUOVgb restoreAutomatically: https://drive.google.com/open?id=1C6KMPW7pezHgYrXe6ZU8JF9kk0Or0Gww ipad: restoreManually: https:https://drive.google.com/open?id=10He9kWygcCVaD0zA5Yc-ctUTCq8HSJP- restoreAutomatically: iphone 5s: restoreManually: https://drive.google.com/open?id=1J2QVm5nZPxPOffQEEhnb-ZohQ0u5l49L restoreAutomatically: https://drive.google.com/open?id=1cSSG9s7urwYJ7SblxF2oqVy8QtfAP1ga
|  | 45003 | restore failed | if user id has expired subscription, user will get restore failed popup message and app | click on restore button, it can be done in downloaded app or new downloaded. | valid user id and password | if user id has expired subscription, user will get restore failed popup message and app | user has got restore failed popup message and app | passed | Fahad Hossain Akash | 2019-03-07 | iphone 5s iphone X ipad | 1. after fresh build, if user is subscription expired the app will say restore failed after pressing restore button | cannot save recording due to lack of time as this test case was able to test in last day
|  | 41002 | subscription expired | if user id has expired subscription, app will be automatically unsubscibed app | after subscribe the app, wait for the expiration | valid user id and password | subscription will be expired once and app will be automatically unsubscibed app | app has been beautomatically unsubscibed app | passed | Fahad Hossain Akash | 2019-02-07 | iphone 5s iphone X ipad |  | iphone X: https://drive.google.com/open?id=1zZapZFk7LB-iLpYNfEARRqfwPeSSpNdG ipad: https://drive.google.com/open?id=1eD1VjjUEwynb91Cxj2smtGspDS11uTA9 iphone 5s: https://drive.google.com/open?id=16AFcTfyvCL76-RxS8rv3-VGWotL-Q3El
4 | server value check | 21503 | subs home after launch the app | subs home will be appear after launch the app | launch the app the app after deleting the app from background | subs home = 1 | subs home will be appear after launch the app | subs home has appear after launch the app | passed | Fahad Hossain Akash | 2019-03-07 | iphone 5s ipad iphone X | 1. no subs home in block list country 2. no cross button when extra column 4 = 1 3. no subs home if subs home= 0 | iphone X: https://drive.google.com/open?id=1ZbAuglV4rgp6mXKA6KiD0ShF5u41gwIF ipad: https://drive.google.com/open?id=1gaifB1YscCXGr9ZmWunnTfXuet5_oBW2 iphone 5s: https://drive.google.com/open?id=12QQeUV3J1NqJzx6hSsBliZ4SFxuscowt
|  | 30003 | Force review against subs page & free server | user can see Force review againts cross button of subs page & free server | device date and country should be non block list country. Click button of any possible way to appear subs page. Click cross button. | isApprv= 1 review unlock = 1 | Force review will be showed againts cross button of subs page & free server | Force review comes againts cross button of subs page & free server | passed | Fahad Hossain Akash | 2019-03-07 | iphone 5s ipad iphone X | 1. no review in block list country 2. no review if review unlock = 0 or isApprv = 0 3. no review is being showed after rating from settings 4. app is purchased after giving force review | iphone X: https://drive.google.com/open?id=1DKs2xtq9gqkzmTinl_PZDTYIBmhDk0ON appPurchased: https://drive.google.com/open?id=1ybsJkg101DD9nQUDnr5Ua6JI1DExg5SB ipad: https: https://drive.google.com/open?id=1FnoPe9ChRvrv-hgOl7OxyPCBw-Lutno0 iphone 5s: https://drive.google.com/open?id=1FJyOY7BpLNv_J9gP7z4wxwjayhaX0xgA appPurchased: https://drive.google.com/open?id=1n0ElhA8l1OON_7mDaZw1BKhYL-D84RzQ
|  | 33003 | subs button changes according to server value | subs button changes according to server value | put value 1 for "start free trial" or put value 0 for "Subscribe now" | extra column 2 = 1/0 isApprv = 1/0 | subs button will be changedaccording to server value | subs button has changed according to server value | passed | Fahad Hossain Akash | 2019-03-07 | iphone 5s ipad iphone X | 1. same behavior in block list country 2. same behabior in crossless subs page 3. if isApprv = 0 or Extra column 2 = 0, Button wont change. It remains "subscribe now" | iphone X: https://drive.google.com/open?id=1pQ0a_4hRLArg-AW9e0eD2RGFv8jObg2u ipad: https://drive.google.com/open?id=1zzTRTISh7JobErR2Xyv7LCQ7EFPVu9jK iphone 5s: https://drive.google.com/open?id=1yF0mrvJEsIk-19HBl6N25ZDHqU6GYgfi
|  | 43003 | VPN connection free session | user can use particuler server for vpn connection with free session | click on free server. Vpn will be connected with free session alert message | extra column 3 = free vpn connection time in sec. | vpn will be connected for certain time according to server value | vpn is connected for certain time according to server value | passed | Fahad Hossain Akash | 2019-03-07 | iphone 5s ipad iphone X | 1. after free session is over, subs page with free session expired alert will be appeared if connection utton is pressed | iphone X: https://drive.google.com/open?id=1V9UgTqFlwKkV9cyIFuFTaQCgaPova3g5 ipad: https://drive.google.com/open?id=1n4V4UIMPy-qMemydBn2CluwmCCI2zHQg iphone 5s: https://drive.google.com/open?id=1N-dBfI9I7fVqdR_pVjcdl0pKbv4VohXH